## OVERVIEW
Summary: 19/20 Representation Work Plan
|  | Who | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | KEY
Planning
| Business as usual (in no particular order) | [16 empty] | Ligher
B1 | Academic Rep Network support | Lucy | [15 empty] | Heavier
B2 | Wellbeing Rep Network support | Gabi | [15 empty] | TBC as new team
B3 | LCO support | Gabi | [15 empty] | Paused
B4 | LCO comms | Gabi
B5 | Committee support (ERB & CWB) | Lucy/Gabi
B7 | Elections | Kristie
B8 | Council
Projects (Cyclical)
P1 | NSS | Lucy
P2 | PRES/PTES | Lucy
P3 | Rep Training | Lucy/Gabi
P4 | Autumn Elections (inc. By-elections & Horizons) | Lucy/Kristie
P5 | SACAS | Lucy/Kristie
P6 | Leadership Elections | Lucy/Kristie
Projects (One-off)
P10 | Rep Experience (support, training, comms. & recognition) | Kristie
P11 | WBRN Review | Gabi
P12 | Rep of the Month | Lucy
P13 | Student Wins | Lucy
P14 | Campaigns system & support | Gabi
P15 | Online petitions system | Lucy

## Plan
ID | FOR YOUR | Target | Outcome | ARN/WRN | LCOs | CU Exec | Responsible | Accountable | Dependencies | Month | Progress | Notes
1 | SUPPORT | Offer dedicated 1-2-1 support to Senior Reps | Monthly/termly catch-ups with Representation Team Staff member/DPW/DPE/Union President |  | X | X | LR/GF | KT | Representation | 2019-11-01 | Complete | Ongoing | Not started
[9 empty] | Officer Trustees |  |  |  | In progress
2 | SUPPORT | Secure a computer with appropriate software (InDesign) for volunteers to create marketing assets | Mac on Level 2M (Union Building) | X | X | X | KM | KT | Marketing | 2019-12-01 | In progress | Waiting on purchase of new macs by KM to repurpose old macs | Complete
[9 empty] | Systems |  |  |  | On hold
3 | SUPPORT | Provide senior volunteers access to Union direct-marketing account to streamline communication with members | Mailchimp access to Union CU/LCO membership mailing list |  | X | X | KM | KT | Marketing | 2019-12-01 | In progress | Responsibility moved to KT to write data sharing protocol to be reviewed by KL
Systems
4 | SUPPORT | Provide senior volunteers editing rights to relevant section of Union website | Editing rights to CU pages and LCO pages (Union website) |  | X | X | PS | KT | Systems | 2019-12-01 | In progress | 0
5 | SUPPORT | Provide senior volunteers access to Union Marketing calendar | Viewing rights to Union Marketing calendar |  | X | X | KM | KT | Marketing | 2019-12-01 | In progress | 0
6 | SUPPORT | Offer systems-specific support for Senior Reps | Systems team termly drop-ins; website ‘how-to’ guidance |  | X | X | PS | KT | Systems | 2019-01-01 | On hold | Paused due to absense of Systems Manager
7 | SUPPORT | Offer finance-specific training support for Senior Reps | Finance team termly drop-ins with DPFS |  | X | X | NG | KT | Finance | 2019-01-01 | On hold | Paused due to capacity changes within Finance team
DPFS
8 | SUPPORT | Consider budgetary needs of Rep support | Consultation of Reps with CU support considered alongside LCOs in departmental budgeting |  | X | X | KT | KT | Finance | 2019-01-01 | Not started | Start in lead up to department budget planning
9 | SUPPORT | Improve access to online information and guidance for Reps | Role-specific collections with associated e-Learning for different Rep roles | X | X | X | LR/GF | KT | Systems | 2019-03-01 | Not started | 0
10 | SUPPORT | Plan out communications for Academic & Wellbeing Rep Networks (Year Reps), Departmental Reps, Faculty Reps (CU Officers), CU Presidents and LCOs | Rep Communications Plan | X | X | X | KM | KT | Marketing | 2019-12-19 | In progress | 0
11 | DEVELOPMENT | Offer design training to up-skill volunteers in creating their own marketing assets | Marketing team-led course on InDesign | X | X | X | KM | KT | Systems | 2019-12-01 | On hold | On hold as relies on availability of Mac on 2M
12 | DEVELOPMENT | Offer training workshops on Communications planning and delivery | Marketing team-led training on communications | X | X | X | KM | KT | Marketing | 2019-12-01 | In progress | Scope changed from in-person session to online guidence via Training Hub
13 | DEVELOPMENT | Offer training to improve volunteers confidence in tackling difficult situations, particularly where behaviour is not considered inclusive | Active By-stander training for Representatives | X | X | X | KT | KT | Representation | 2019-01-01 | On hold | Paused due to absense of Student Development Manager
Student Development
14 | VOICE | Improve communication of ‘Rep Wins’ across College | ‘Rep Wins’ marketing assets created; regularly scheduled posts (monthly) to promote via Union SM channels | X | X | X | LR | KT | Marketing | 2019-11-01 | In progress | Feasibility for integration with Drupal8 with page on website used in interim
15 | VOICE | Improve recognition of Rep successes within both Academic & Wellbeing Rep Networks | ‘Rep of the month’ scheme, promoted via Union SM channels and monthly Rep e-newsletter | X |  |  | LR | KT | Marketing | 2019-11-01 | Complete | Ongoing
16 | VOICE | Improve Senior Rep’s understanding of Union-wide developments to improve transparency of partnership between Union and Constituent Unions (CUs) | Termly Senior Rep Briefings for CU Presidents |  |  | X | KL | KT | Marketing | 2019-12-01 | Complete | Ongoing
17 | VOICE | Improve promotion of Representation via Union Social Media | Review Senior Rep access to Union SM (Bars & Takeovers) |  | X | X | KM | KT | Marketing | 2019-12-01 | Complete | 0
18 | VOICE | Improve collaboration between Representation and Marketing teams to ensure effective promotion of Representation and activities of our Rep Networks | Schedule monthly Representation & Marketing meeting to discuss Representation needs | X | X | X | KM/KT | KT | Marketing | Ongoing | Complete | 0

## Support
ID | Project steps | RM | MCM | RCE | RCW | HoSVC | LCOs | CUs | ARN | WRN | Systems | FM | ASM | SDM | DPW | DPE | Pres | Progress | Notes
1 | Create and send out doodle poll to CU Presidents | A |  | R |  |  |  | I | [7 empty] | I | C/I | Complete | Ongoing | KEY
| Create and send out doodle poll to LCOs | A |  |  | R |  | I | [7 empty] | I |  |  | Complete
| Create agenda template with rolling discussion points | A |  |  | R |  | I | I | [6 empty] | C |  |  | Complete |  | RM | Representation Manager
| Send record of 1-1 and store in SharePoint | A |  | R | R |  | I | I | [6 empty] | I | I | I | In progress |  | MCM | Marketing & Comms Manager
2 | Determine system requirements | A | R |  |  |  | C | C | C | C | I |  | I |  |  |  |  | In progress | Waiting on purchase of new macs by KM to repurpose old macs | RCE | Representation Coord (Education)
| Order new macs | A | R | [7 empty] | C | [6 empty] | In progress |  | RCW | Representation Coord (Wellbeing)
| Liaise with relevant staff to fit in with office move schedule | A | R | [7 empty] | C |  | C |  |  |  |  | Not started |  | HoSVC | Head of Student Voice & Comms
| Agree rota/booking system | A | C |  | R |  | I | I | I | I | C | [6 empty] | Not started |  | LCOs | Liberation & Community Officers
| Communicate system to Reps | A |  |  | R |  | I | I | I | I | [7 empty] | Not started |  | CUs | Constituent Union Executives
3 | Create Mailchimp list protocol for data sharing | A |  |  |  | R | I | I | [9 empty] | Not started | Responsibility moved to KT to write data sharing protocol to be reviewed by KL | ARN | Academic Rep Network
| Create 'How-to' guide for mailing list use (comms. guidelines) | A | R | [14 empty] | Not started |  | WRN | Wellbeing Rep Network
| Agree and communicate process inc. validation quiz | A | C |  | R |  | I | I | [6 empty] | I | I | I | Not started |  | FM | Finance Manager
4 | Meet with Systems to determine feasability | A/R | [8 empty] | C | [6 empty] | Complete |  | ASM | Administration Support Manager
| Build into Rep team internal comms. plan | A |  |  | R | [9 empty] | I | I | I | In progress |  | SDM | Student Development Manager
| Contact reps to ask for amended content for edits | A |  |  | R |  | C | C | [9 empty] | Not started |  | DPW | Deputy President (Welfare)
| Make edits on LCO pages | A |  |  | R |  | I | [10 empty] | Not started |  | DPE | Deputy President (Education)
| Make edits on CU pages | A |  | R |  |  | I | [10 empty] | Not started |  | Pres | Union President
5 | Share calendar with Kristie to assess value of resource | A | R | [14 empty] | Complete
| Create calendar within Rep team 'Teams' or repstaff calendar | A |  |  | R | [5 empty] | C |  |  |  | I | I | I | In progress |  | Not started | R | Responsible
| Share calendar with reps | A |  | R | R | [12 empty] | Not started |  | In progress | A | Accountable
6 | Discuss feasability with Systems | A/R | [8 empty] | C | [6 empty] | Complete | Paused due to absense of Systems Manager | Complete | C | Consult
| Make amendments to ‘Data Protection’ section of existing training | A/R | [15 empty] | Not started |  | On hold | I | Inform
| Add in trainer notes to SharePoint section | A | [8 empty] | R | [6 empty] | Not started
| Share Repstaff Teams with Systems to incorperate into training | A |  | R | [13 empty] | Not started
| Send poll to Reps to gauge interest and availability | A |  | R | R |  | I | I | I | I | [7 empty] | Complete
| Book date for training and deliver | A/R | [8 empty] | R | [6 empty] | In progress
7 | Discuss feasability with Finance | A/R | [9 empty] | C | [5 empty] | Complete | Paused due to capacity changes within Finance team
8 | Contact reps for feedback on budget alloctation for 20/20 | A |  | R | R |  | C | C | [9 empty] | Not started
| Include in E&W (Rep) budget 20/20 | A/R | [15 empty] | Not started
9 | Review and update existing content: ARN | A |  | R | [13 empty] | Not started
| Review and update existing content: WBRN | A |  |  | R | [12 empty] | Not started
| Review and update existing content: CUs | A/R | [5 empty] | I | [8 empty] | C | Not started
| Create associated quiz via Forms to track completion of online 'training' | A |  | R | R |  |  |  | I | I | [7 empty] | Complete
10 | Meet with Marketing to discuss | A/R | C | [14 empty] | Complete
| Create LCO specific plan | A | C |  | R |  | I | [7 empty] | C |  |  | In progress
| Create CU specific plan | A/R | C |  |  | C |  | I | [7 empty] | C | C | Not started
| Create WBRN specific plan | A | C |  | R |  |  |  |  | I |  |  |  |  | C |  |  | Not started
| Create ARN specific plan | A | C | R |  |  |  |  | I | [6 empty] | C |  | Not started
| Combine to Representation plan | A/R | [15 empty] | Not started

## Devel.
ID | Project steps | RM | MCM | RCE | RCW | HoSVC | LCOs | CUs | ARN | WRN | Systems | FM | ASM | SDM | DPW | DPE | Pres | Progress | Notes
11 | Determine feasability with Marketing | A/R | C | [14 empty] | Complete | On hold as relies on availability of Mac on 2M | KEY
| Discuss holding a one-off workshop run by Senior Designer | A | R | [14 empty] | Complete |  | RM | Representation Manager
| Design session plan | A/R | C | [14 empty] | Not started |  | MCM | Marketing & Comms Manager
| Send poll to Reps to gauge interest and availability | A |  | R | R |  | I | I | I | I | [7 empty] | Not started |  | RCE | Representation Coord (Education)
| Book date for training and deliver | A/R | C | [14 empty] | Not started |  | RCW | Representation Coord (Wellbeing)
12 | Determine feasability with Marketing | A | [15 empty] | Complete | Scope changed from in-person session to online guidence via Training Hub | HoSVC | Head of Student Voice & Comms
| Look at rep feedback and provide scope for training workshop | A/R | [15 empty] | In progress |  | LCOs | Liberation & Community Officers
| Create training plan | A/R | R | [14 empty] | Not started |  | CUs | Constituent Union Executives
| Send poll to Reps to gauge interest and availability | A |  | R | R |  | I | I | I | I | [7 empty] | Not started |  | ARN | Academic Rep Network
| Book date for training and deliver | A |  |  |  |  | I | I | I | I | [7 empty] | Not started |  | WRN | Wellbeing Rep Network
13 | Determine feasability with Student Development | A/R | [11 empty] | C |  |  |  | Not started | Paused due to absense of Student Development Manager | FM | Finance Manager
[20 empty] | ASM | Administration Support Manager
[20 empty] | SDM | Student Development Manager
[20 empty] | DPW | Deputy President (Welfare)
[20 empty] | DPE | Deputy President (Education)
[20 empty] | Pres | Union President
[20 empty] | Not started | R | Responsible
[20 empty] | In progress | A | Accountable
[20 empty] | Complete | C | Consult
[21 empty] | I | Inform

## Voice
ID | Project steps | RM | MCM | RCE | RCW | HoSVC | LCOs | CUs | ARN | WRN | Systems | FM | ASM | SDM | DPW | DPE | Pres | Progress | Notes
14 | Agree marketing needs | A | C | R | [13 empty] | Complete | Feasibility for integration with Drupal8 with page on website used in interim | KEY
| Meet with systems to determine system requirements | A | C | R | [13 empty] | In progress
| Create page on Union website to house wins | A | C | R |  |  | I | I | I | I | [7 empty] | In progress
| Build into Union SM communications plan: regular posting (termly) | A | R | C | [13 empty] | Not started |  | RM | Representation Manager
15 | Agree marketing needs | A | C | R | [13 empty] | Complete |  | MCM | Marketing & Comms Manager
| Agree criteria and format with Reps | A |  | R | C |  |  |  | C | C |  |  |  |  | C | C |  | Complete |  | RCE | Representation Coord (Education)
| Create webform for nomination/voting process | A |  | R | [13 empty] | Complete |  | RCW | Representation Coord (Wellbeing)
| Sign off on designs | A/R |  | C |  | C | [11 empty] | Complete |  | HoSVC | Head of Student Voice & Comms
| Build into Union SM communications plan: regular posting (monthly) | A | R | I | [13 empty] | In progress |  | LCOs | Liberation & Community Officers
| Create 'How-to' for process | A | C | R | [13 empty] | Complete |  | CUs | Constituent Union Executives
16 | Agree and book in date(s) for termly briefings | A |  |  |  | R |  | C | [9 empty] | In progress |  | ARN | Academic Rep Network
| Prepare agenda | A/I |  |  |  | R | [11 empty] | Not started |  | WRN | Wellbeing Rep Network
| Communicate Agenda | A |  |  |  | R |  | I | [9 empty] | Not started |  | FM | Finance Manager
| Write up and share any actions | A/R | [5 empty] | I | [9 empty] | Not started |  | ASM | Administration Support Manager
17 | Determine requirements & process for SM 'takeovers' | A |  |  | R | [9 empty] | C |  |  | Complete |  | SDM | Student Development Manager
| Create request form (online) | A | R | I | I | [12 empty] | Complete |  | DPW | Deputy President (Welfare)
| Communicate to reps | A |  | R | R |  | I | I | I | I | [7 empty] | Complete |  | DPE | Deputy President (Education)
18 | Schedule monthly meetings | A | R | [14 empty] | Complete |  | Pres | Union President
[20 empty] | Not started | R | Responsible
[20 empty] | In progress | A | Accountable
[20 empty] | Complete | C | Consult
[21 empty] | I | Inform